## Forward Traceability
Requirements | Tests | Executions | Defects
SJV-24 - [Reddit][Search bar] There needs to be an auto-fill function when writing any word in the search bar | SJV-27 - Verify that you can enter any character input in the search bar | Reddit Search bar - PASS | None
| SJV-28 - Verify that the list of queries update depending on the word in the search bar | Reddit Search bar - PASS | None
| SJV-29 - Verify that each item in the list of auto-fill links correctly to the page of the community/user | Reddit Search bar - PASS | None
| SJV-30 - Verify that only users are listed when entering "u/" at the beginningof the search bar | Reddit Search bar - FAIL | SJV-36 - Backlog - [Reddit][Search bar] Communities can also appear in the search list when beginning the query with "u/"
| SJV-31 - Verify that only communities are listed when entering "r/" at the beginningof the search bar | Reddit Search bar - FAIL | SJV-35 - Backlog - [Reddit][Search bar] Users can also appear in the search list when beginning the query with "r/"
SJV-23 - [Reddit][Search bar] A list of trending topics for the day is presented to the user after clicking the search bar | SJV-25 - Verify that you can see the list of trending topics when pressing click on the search bar | Reddit Search bar - PASS | None
| SJV-26 - Verify the a user can click on a post from the trending list to access the page for the topic | Reddit Search bar - PASS | None
| SJV-32 - Verify that you can see the most recent history of the pages access on the website when clicking on the search bar | Reddit Search bar - PASS | None
| SJV-33 - Verify that a maximum of 3 entries appear in the recent history of the search bar | Reddit Search bar - FAIL | SJV-34 - In Progress - [Reddit][Search bar] Recent history for the search bar can show more than 3 entries
|  | Reddit Search bar - FAIL | SJV-34 - In Progress - [Reddit][Search bar] Recent history for the search bar can show more than 3 entries - step level
SJV-12 - [Reddit] Popular communities tab | SJV-37 - Verify that the Popular community tab can be expanded and collapse | Popular communities - PASS | None
| SJV-38 - Verify that the list of entries for the popular community tab shows different communities when reloading the page | Popular communities - PASS | None
| SJV-39 - Verify that the subreddits from the popular community tab can be accessed | Popular communities - PASS | None